## Plan
Business Objective
Since acquiring new customer is expensive (costs 5-10 times more), we need to retain as many as we can.
Therefore SENSITIVITY rate should be high.
Churn Type: Usage based
Customer Type |  | Churn needs to be predicted for High Value Customer only
High Value Customer
Regular Customer
Customer Life Cycle
Good | first 2 months
Action | 3rd month is action phase |  |  | Assumption for a trend: |  | After a customer calls the call center (mostly to report an issue) his usage will drop (not sure if we'll be able to use it in the final model).
Churn | 4th month is Churn phase
High level plan
Data Analysis | 1 | Pre processing |  |  | Expected output: | Should have quality data in hand (as per assignment's requirements) by Wednesday EOD (13-Mar-2019).
|  | 1.1 | Data Analysis
|  |  | 1.1.1 | Understand the purpose of the fields and its relavence on the model
|  |  | 1.1.2 | Identify if certain columns can be associated with customer lifecycle.
|  |  | 1.1.3 | Assume trends based on business understanding and validate with the data
|  |  | 1.1.4 | Identify fields which are unnecessary
|  | 1.2 | Keep data of high value customers, delete rest.
|  | 1.3 | Treat columns with missing values (replace or drop)
| 2 | EDA
|  | 2.1 | Study Class Imbalance
|  | 2.2 | Perform EDA and analysis on uni and/or bivariate variables, wherever necessary.
|  | 2.3 | Identify / Derive new features (if possible)
|  | 2.4 | Perform PCA to reduce the number of variables.
Model Building and Verification | 3 | Model Building and Verification
|  | 3.1 | Model building
|  |  | 3.1.1 | Build a Logistic Regression Model
|  | 3.2 | Model evaluation
|  |  | 3.2.1 | Prepare Confusion Matrix
|  |  | 3.2.2 | Prepare ROC curve
|  |  | 3.2.3 | Choose the right model
High level Schedule
2019-03-11 | 2019-03-12 | 2019-03-13 | 2019-03-14 | 2019-03-15 | 2019-03-16 | 2019-03-17
Data pre-processing |  |  | EDA | PCA | MODEL Building and verification | Contingency day
RAID Analysis
Risks | [6 empty] | Mitigation
1 | To many versions of code. | [5 empty] | 1 | Maintain code in Git repository.
2 | Ppl at different location, hence won't be able to work together in a war room scenario. | [5 empty] | 2.1 | Should target to finish the assignment by Saturday (16-Mar) to have an entire day, for any contingency.
[7 empty] | 2.2 | Keep everyone updated on your daily progress.
[7 empty] | 2.3 | Raise issues immediately so that others can help, if required. Or are at least aware of it.
[7 empty] | 2.4 | Clear understanding and segregation of tasks. (please raise your hands in case of any issues)
3 | Implicit assumptions or Assumptions made in silo. | [5 empty] | 3 | Call out each and every assumption. If possible, write in the top of Python notebook.
4 | Since most of the tasks have hard dependency on the previous tasks, task division and scheduling may be a problem. | [5 empty] | 4.1 | Plan for short duration
[7 empty] | 4.2 | Plan backwards
5 | As this point in time only part of the plan is finalised. | [5 empty] | 5 | Keep updating and publishing the plan regularly. | Owner: | Amar (with guidance from Femida)
Assumptions
1 | Everyone has gone through the Data, Data dictionary, Problem statement, and Evaluation Rubrics. | [5 empty] | 1 | if not, then please go through.
2 | That the assignment will be completed on time. | [5 empty] | 2.1 | Check progress on daily basis.
[7 empty] | 2.2 | Identify quality metrics.
3 | Everyone has acess to internet, and sharing of information can happen on real time.
Issues
1
Dependencies
1 | Git is available to all and at all times. | [5 empty] | 1 | Let know if there is any access issues.
Details for Git Repository
URL | https://github.com/amar198/ML_Assignment
User name | amar198@gmail.com
Password | 1P@ssword9
Note on D31: Will Naive Baise be required for Model Building or Evaluation?
Note on H40: No major task should be pending on this date.

## Field Analysis
Outlier Check
Fields | Description | Type | Missing Values | Unique Values | Mean | Median | Mode | IRQ | Field Type
mobile_number | Others | [7 empty] | Categorical - Unordered
circle_id | Others | [7 empty] | Categorical - Ordered
loc_og_t2o_mou | Outgoing | [7 empty] | Numerical
std_og_t2o_mou | Outgoing | [7 empty] | Text
loc_ic_t2o_mou | Incoming
last_date_of_month_6 | Revenue
last_date_of_month_7 | Revenue
last_date_of_month_8 | Revenue
last_date_of_month_9 | Revenue
arpu_6 | Revenue
arpu_7 | Revenue
arpu_8 | Revenue
arpu_9 | Revenue
onnet_mou_6 | Internet
onnet_mou_7 | Internet
onnet_mou_8 | Internet
onnet_mou_9 | Internet
offnet_mou_6 | Internet
offnet_mou_7 | Internet
offnet_mou_8 | Internet
offnet_mou_9 | Internet
roam_ic_mou_6 | Incoming
roam_ic_mou_7 | Incoming
roam_ic_mou_8 | Incoming
roam_ic_mou_9 | Incoming
roam_og_mou_6 | Outgoing
roam_og_mou_7 | Outgoing
roam_og_mou_8 | Outgoing
roam_og_mou_9 | Outgoing
loc_og_t2t_mou_6 | Outgoing
loc_og_t2t_mou_7 | Outgoing
loc_og_t2t_mou_8 | Outgoing
loc_og_t2t_mou_9 | Outgoing
loc_og_t2m_mou_6 | Outgoing
loc_og_t2m_mou_7 | Outgoing
loc_og_t2m_mou_8 | Outgoing
loc_og_t2m_mou_9 | Outgoing
loc_og_t2f_mou_6 | Outgoing
loc_og_t2f_mou_7 | Outgoing
loc_og_t2f_mou_8 | Outgoing
loc_og_t2f_mou_9 | Outgoing
loc_og_t2c_mou_6 | Outgoing
loc_og_t2c_mou_7 | Outgoing
loc_og_t2c_mou_8 | Outgoing
loc_og_t2c_mou_9 | Outgoing
loc_og_mou_6 | Outgoing
loc_og_mou_7 | Outgoing
loc_og_mou_8 | Outgoing
loc_og_mou_9 | Outgoing
std_og_t2t_mou_6 | Outgoing
std_og_t2t_mou_7 | Outgoing
std_og_t2t_mou_8 | Outgoing
std_og_t2t_mou_9 | Outgoing
std_og_t2m_mou_6 | Outgoing
std_og_t2m_mou_7 | Outgoing
std_og_t2m_mou_8 | Outgoing
std_og_t2m_mou_9 | Outgoing
std_og_t2f_mou_6 | Outgoing
std_og_t2f_mou_7 | Outgoing
std_og_t2f_mou_8 | Outgoing
std_og_t2f_mou_9 | Outgoing
std_og_t2c_mou_6 | Outgoing
std_og_t2c_mou_7 | Outgoing
std_og_t2c_mou_8 | Outgoing
std_og_t2c_mou_9 | Outgoing
std_og_mou_6 | Outgoing
std_og_mou_7 | Outgoing
std_og_mou_8 | Outgoing
std_og_mou_9 | Outgoing
isd_og_mou_6 | Outgoing
isd_og_mou_7 | Outgoing
isd_og_mou_8 | Outgoing
isd_og_mou_9 | Outgoing
spl_og_mou_6 | Outgoing
spl_og_mou_7 | Outgoing
spl_og_mou_8 | Outgoing
spl_og_mou_9 | Outgoing
og_others_6 | Outgoing
og_others_7 | Outgoing
og_others_8 | Outgoing
og_others_9 | Outgoing
total_og_mou_6 | Outgoing
total_og_mou_7 | Outgoing
total_og_mou_8 | Outgoing
total_og_mou_9 | Outgoing
loc_ic_t2t_mou_6 | Incoming
loc_ic_t2t_mou_7 | Incoming
loc_ic_t2t_mou_8 | Incoming
loc_ic_t2t_mou_9 | Incoming
loc_ic_t2m_mou_6 | Incoming
loc_ic_t2m_mou_7 | Incoming
loc_ic_t2m_mou_8 | Incoming
loc_ic_t2m_mou_9 | Incoming
loc_ic_t2f_mou_6 | Incoming
loc_ic_t2f_mou_7 | Incoming
loc_ic_t2f_mou_8 | Incoming
loc_ic_t2f_mou_9 | Incoming
loc_ic_mou_6 | Incoming
loc_ic_mou_7 | Incoming
loc_ic_mou_8 | Incoming
loc_ic_mou_9 | Incoming
std_ic_t2t_mou_6 | Incoming
std_ic_t2t_mou_7 | Incoming
std_ic_t2t_mou_8 | Incoming
std_ic_t2t_mou_9 | Incoming
std_ic_t2m_mou_6 | Incoming
std_ic_t2m_mou_7 | Incoming
std_ic_t2m_mou_8 | Incoming
std_ic_t2m_mou_9 | Incoming
std_ic_t2f_mou_6 | Incoming
std_ic_t2f_mou_7 | Incoming
std_ic_t2f_mou_8 | Incoming
std_ic_t2f_mou_9 | Incoming
std_ic_t2o_mou_6 | Incoming
std_ic_t2o_mou_7 | Incoming
std_ic_t2o_mou_8 | Incoming
std_ic_t2o_mou_9 | Incoming
std_ic_mou_6 | Incoming
std_ic_mou_7 | Incoming
std_ic_mou_8 | Incoming
std_ic_mou_9 | Incoming
total_ic_mou_6 | Incoming
total_ic_mou_7 | Incoming
total_ic_mou_8 | Incoming
total_ic_mou_9 | Incoming
spl_ic_mou_6 | Incoming
spl_ic_mou_7 | Incoming
spl_ic_mou_8 | Incoming
spl_ic_mou_9 | Incoming
isd_ic_mou_6 | Incoming
isd_ic_mou_7 | Incoming
isd_ic_mou_8 | Incoming
isd_ic_mou_9 | Incoming
ic_others_6 | Incoming
ic_others_7 | Incoming
ic_others_8 | Incoming
ic_others_9 | Incoming
total_rech_num_6 | Revenue
total_rech_num_7 | Revenue
total_rech_num_8 | Revenue
total_rech_num_9 | Revenue
total_rech_amt_6 | Revenue
total_rech_amt_7 | Revenue
total_rech_amt_8 | Revenue
total_rech_amt_9 | Revenue
max_rech_amt_6 | Revenue
max_rech_amt_7 | Revenue
max_rech_amt_8 | Revenue
max_rech_amt_9 | Revenue
date_of_last_rech_6 | Revenue
date_of_last_rech_7 | Revenue
date_of_last_rech_8 | Revenue
date_of_last_rech_9 | Revenue
last_day_rch_amt_6 | Revenue
last_day_rch_amt_7 | Revenue
last_day_rch_amt_8 | Revenue
last_day_rch_amt_9 | Revenue
date_of_last_rech_data_6 | Revenue
date_of_last_rech_data_7 | Revenue
date_of_last_rech_data_8 | Revenue
date_of_last_rech_data_9 | Revenue
total_rech_data_6 | Revenue
total_rech_data_7 | Revenue
total_rech_data_8 | Revenue
total_rech_data_9 | Revenue
max_rech_data_6 | Revenue
max_rech_data_7 | Revenue
max_rech_data_8 | Revenue
max_rech_data_9 | Revenue
count_rech_2g_6 | Revenue
count_rech_2g_7 | Revenue
count_rech_2g_8 | Revenue
count_rech_2g_9 | Revenue
count_rech_3g_6 | Revenue
count_rech_3g_7 | Revenue
count_rech_3g_8 | Revenue
count_rech_3g_9 | Revenue
av_rech_amt_data_6 | Revenue
av_rech_amt_data_7 | Revenue
av_rech_amt_data_8 | Revenue
av_rech_amt_data_9 | Revenue
vol_2g_mb_6 | Internet
vol_2g_mb_7 | Internet
vol_2g_mb_8 | Internet
vol_2g_mb_9 | Internet
vol_3g_mb_6 | Internet
vol_3g_mb_7 | Internet
vol_3g_mb_8 | Internet
vol_3g_mb_9 | Internet
arpu_3g_6 | Revenue
arpu_3g_7 | Revenue
arpu_3g_8 | Revenue
arpu_3g_9 | Revenue
arpu_2g_6 | Revenue
arpu_2g_7 | Revenue
arpu_2g_8 | Revenue
arpu_2g_9 | Revenue
night_pck_user_6 | Internet
night_pck_user_7 | Internet
night_pck_user_8 | Internet
night_pck_user_9 | Internet
monthly_2g_6 | Internet
monthly_2g_7 | Internet
monthly_2g_8 | Internet
monthly_2g_9 | Internet
sachet_2g_6 | Internet
sachet_2g_7 | Internet
sachet_2g_8 | Internet
sachet_2g_9 | Internet
monthly_3g_6 | Internet
monthly_3g_7 | Internet
monthly_3g_8 | Internet
monthly_3g_9 | Internet
sachet_3g_6 | Internet
sachet_3g_7 | Internet
sachet_3g_8 | Internet
sachet_3g_9 | Internet
fb_user_6 | Internet
fb_user_7 | Internet
fb_user_8 | Internet
fb_user_9 | Internet
aon | Others
aug_vbc_3g | Internet
jul_vbc_3g | Internet
jun_vbc_3g | Internet
sep_vbc_3g | Internet